## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Login and registration forms | Yes | Yes | High | Complete | 4 | Yes
Signup | Yes | Yes | High | Complete | 1 | Yes
Login | Yes | Yes | Medium | Complete | 1 | Yes
Vechile registration form | Yes | Yes | High | Complete | 1 | Yes
Vistor's form | Yes | Yes | Medium | Complete | 1 | Yes
number plate rec. and admin approval | Yes | No | Medium | Complete | 13 | Yes
Can review vechiles | Yes | No | Low | Complete | 1 | Yes
Vechile Number Plate recognization | Yes | Yes | High | Complete | 5 | Yes
Registration Approval | Yes | No | Medium | Complete | 2 | Yes
Extract text from Number plate | No | No | High | Complete | 5 | Yes
security management | Yes | No | Medium | In Progress | 6 | No
Enter Vechicle number to check | Yes | No | Medium | Complete | 2 | Yes
Can enter details of unregistered vechiles | Yes | No | Medium | Complete | 1 | Yes
Mail sending and time noting in every request update | Yes | No | Low | In Progress | 3 | No
vehicle records and extra features | Yes | No | Medium | In Progress | 2.5 | No
Vechile records and Visitor records | Yes | No | Medium | Complete | 1 | No
Adding drafts to registration/ Vistor forms | Yes | Yes | Medium | In Progress | 1.5 | No
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started